## MCC PROGRESS REPORT TEMPLATE

PROJECT AND PARTNER INFORMATION

Date Submitted

5th October 2021

Project Title

Improved Household Food Security and Household Incomes (IHFSHI) in Lobanya community

Project Number

N/A

Project Location
Lobanya Community, Kacheri Sub County, Kotido District

Partner Organization Name

Diocesan Development Services-North Karamoja (DDS-NK)

Report Author/s

Ogwaria Moris, Project Officer DDS-NK

Report Reviewer/s
Komakech Wilfred (Programme Manager), Ijala Simon Peter (Executive Director DDS-NK)

Time period covered by the report

Start date: 1st July 2021					End date: 30th September 2021

PROJECT WORK UPDATE

- Community Changes

- Insecurity: This has been a continual act within the communities round the implementation area, now that the kraals are migrating to this community, there is a very great threat to live and property of community especially households with animals. Late August about 1.5 herds of cattle (1,500) were raided from the kraal around Maur by the Dodoth warriors, there were no life lost, but a serious threat to security in Kacheri since they use corridors of Lobanya to drive the cows. In Lobanya the Dodoth warriors looted the home of the former LCI and took most of his properties; food, chicken, Clothes this formed him to move to centre for safety.

- Covid 19: the pandemic has really caused a surge in participants well-being/fear since the standards of living has raised economically. Market prices have risen making life hard in the rural community

- Wildlife: this is a serious threat to live and property, as we speak now families sleep in their gardens to protect their crops from being destroyed by the elephants, this act as caused a surge in VSLA savings, since most families spend their entire time guarding their crops with no time to look for money to save.

- Learning and unexpected results

Unexpectedly these quarter, famers may receive a lot of harvest from Maize, this is seen from the continual monitoring during support visits done by the project officer.

- Changes to future plans

N/A

- Outcome 1: Increased Crop production by 120 targeted farmers

Activities

Quarterly Review meeting to review the work of the lead farmers

The meeting started with the mobilization of the lead farmers on the 24th/September/2021, in Lobanya and Napetakeru, the actual meeting date was 27th/September/2021, 16 participants (7F, 9M) attended the meeting but 2M participants were follower farmers and was joined by the MCC Uganda country representatives and coordinator. The purpose of the meeting was to review work with the lead farmers,

The best practices practiced by the lead farmers were; conservation agriculture practices, which includes inter cropping, row cropping, mulching, crop rotation, and minimal soil disturbance this was seen in the use of permanent planting basins. They also use pre-liminary measures to guard elephants from their gardens i.e., use of wasted engine oil smeared in the ropes and tied along boundaries, planting hot pepper along the edges of the garden, pillar of fire at night, use of noise.

Amidst all the best practice, there were also bad practices on wasted of grains during drying, this poor post – harvest practice, is basically brought by financial constraints, like tarpaulin and the community store ha been hired to the constructors this also contributed to poor storage of grain. Non the less they have encouraged by project officer to construct local granaries and save some money so that they can buy super grain bags for storage and tarpaulin for drying to reduce on the post-harvest losses.

The action point from the meeting was, maximization of production by opening more land for production, planning in advance for farm operations, like opening of land, planting, weed and pest management, harvest and post-harvest management. Lead farmer were encouraged to manage their harvest properly that is plan for what to sale, eat and keep for seeds in the next planting season.

The meeting was adjourned by individual household harvest monitoring by the Mennonite Central Committee Country representatives and Diocesan Development Services-North Karamoja staff, this visit yielded fruits since farmers were able to testify and also visual aid of stores, and houses also made stores for maize grain. 8 (4M,4F) farmers were visited, 5(3F,2F) were lead farmers and 3 (2M,1F) follower farmers.

Monthly support visit to lead farmers and follower farmers

The project officer made support visits to support them while implementing their activities to make corrections, and give technical advice to the lead farmers, this activity this time was adequately done, though there has been a lot of insecurity threat this created a minimum time in the field. 15(6M, 9F) lead farmers and Follower farmers 91 (37 M, 54 F) lead farmers were supported individually. This activity was done twice a month.

Technical support was on Post harvest handling, Harvest management , weed and pest management, bean agronomy for those that planted late.

The main issues in the field, is the poor storage facilities, poor post-harvest handling, lack of post-harvest handling facilities (drying) and poor harvest management within the community since proceeds are stored in the living rooms. The community pledged if the project would assist them with post-harvest handling facilities like silo’s, tarpaulin, hermetic sacs.

Changes to activities planned this reporting period

N/A

Outcome 2: Improved income by 120 targeted farmers

Support VSLA groups with passbooks

Diocesan Development Services-North Karamoja finance Office outsourced the service provider (Natirai Flying Solutions SMC ltd) to procure the items, the procured items were: 120 passbooks, 4-minute books, 4 Savings Analysis book, and 20 pens.

The project officer distributed the procured items to the various groups of Kaemanik, Korisae, Longayum Napetakeru, and Toiunae farmer groups, each received 30 passbooks, 1 Savings analysis book, 1-minute book and 5 pens on the 26th, August, 2021.

The Project officer also made 6 VSLA support visits to the different savings group of Longayum Napetakeru, Korisae, Kaemanik and Toiunae to ascertain the savings process. The savings this time is not been consistent, since the members have been very committed in their garden work (guarding against wildlife), scarcity of finance, since there has less casual labor that brings money in their hands and effects of Covid-19 Lock down. The savings amounts shall be projected /reported annually.

Conducted training of the VSLA group Executives on VSLA Methodology

The activity started by mobilization of the executives which included Chairperson, Secretary, Treasurer, and 1 key holder representative from each group on 29th/July/2021.The activity was implemented on the 2nd /August/2021 with attendance of 18 (10 F, 8M) inclusive of the project Officer and Facilitator (SCDO Kacheri s/c in Lobanya parish.

The training was guided by two (2) basic objectives; to enable participants, define VSLA and its Importance, to describe the different concepts used in VSLA. The executive expectations were: Knowledge on how to record loans and Knowledge on how to calculate the interest. The facilitator used three (3) training methodologies to help the executives understood the training module and this included: Discussion, Questions and answers and Brainstorming.

The executives were taken through different topics in the VSLA methodology and this included;

Definition of VSLA, Importance of VSLA, Definition of VSLA Concepts, why people save and borrow, VSLA Principles and practices, Type of Records kept in VSLA & Rational for record keeping in VSLA, sharing out, Roles of leaders in VSLA, Challenges/ risks in VSLA, Tips on how to save with a purpose and Tips on How to Manage Personal Finance and Stay Within Your Budget.

The participants understood more on the concept of interest, since before the interest was only shared among those got loans only, they also appreciated the concept of sharing out at the end of every cycles which they did not understood well.

Training of group Executives on Group Dynamics

The activity started by mobilization for the executives which included Chairperson, Secretary, Treasurer from each group on 6th/Aug/2021.The activity was implemented on the 10th /August/2021 with attendance of 14 (6 F, 8M) inclusive of the project Officer and Facilitator (SCDO Kacheri s/c in Lobanya parish.

The training was guided by two (2) basic objectives; to equip participants with skills on Group dynamics and leadership, to come up with action plan and way forward. The participant’s expectations were: Knowledge and skills on group management and leadership, to share experiences and good time management. The facilitator used three (3) training methodologies to help participants understood the training module and this included: Discussion, Questions and answers and Brainstorming.

The participants were taken through different topics in group dynamics and this included; Session 1;

Definition of group dynamics, meaning of a group, stages in group development, conditions that make a group member united, importance of a group, qualities of a good group, difference between a group and gathering, Session 2; conflict management in farmer group, causes of group conflicts, conflict management plan, Conflict resolution process. Session 3; Leadership: who is a leader, types of the leaders, leadership and management practices, management practices, Qualities of good leader, characteristics of good team, and roles of a leader.

Outcome 3: Reduced cases of domestic violence related to handling of crop harvests and incomes

Not applicable in the quarter. No activity under this outcome was conducted.

Participants

| Subsistence farmers (youth, men, women). | # Of People |  |
| --- | --- | --- |
|  | # Women | # Men |
| Subsistence farmers (directly involved) | 80 | 40 |
| Adults (indirect beneficiaries) | 114 | 126 |
| Children (indirect beneficiaries) | 114 | 126 |
| Total Number | 308 | 292 |

- Capacities

N/A

PROJECT MONITORING AND EVALUATING

N/A

FINANCES AND OTHER RESOURCES

| Financial Attach a separate, detailed financial report, comparing cumulative project yearly expenditure against original planned budget. Break down expenditure by activity. Use the currency used for project expenses. Explain any significant variance to the planned budget. | The financial report submitted separated |
| --- | --- |
| Number of and title of seconded personnel | N/A |
| Material/food assistance details | N/A |

STORIES

N/A, this quarter

Appendix: Logical Framework (Logframe)

| Long-term Impact To contribute towards improved food security and sustainable development among the rural households in North Karamoja |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Outcome Indicator | Previous reporting period indicator information (Include baseline) | Current reporting period indicator information Cumulative or current number for longitudinal changes. | Outputs: current reporting period Brief description and number, disaggregated by men and women, if appropriate. | Outputs: Cumulative from project start Brief description and number, disaggregated by men and women, if appropriate. | Bullet point summary list of activities carried out this reporting period. |
| Outcome 1 Increased Crop production by 120 targeted farmers | Kg of simsim, maize, groundnuts and beans per household per season | Simsim: 83.5 kg per household per season Maize: 424.5kg per household per season Groundnuts: 193.4 per household per season Beans 73.6 kg per household per season | This will be collected after all the harvest is done i.e. quarter 3 | N/A 105 participated in the extension Visits by Lead farmers (60 F,45 M) 106 individual received extension visits offered by the project officer (63F, 43M) N/A | 15 individuals attended training in improved agriculture (10F,5M) 105 farmers participated in extension visits offered by lead farmers (60 F,45 M) 120 individuals received extension visits offered by project officer (80F, 40M) | Monthly support to lead farmers and follower farmers by the project officer. 106 farmers supported (63F, 43M) Conduct Quarterly meeting and monitoring by board members, project staffs and District Officials 7(5M,2F) Quarterly meeting for reviewing work of lead farmers 16(7F,9M) |
|  | # of months of food produced from harvest by household type | 6 months for Simsim per household 8 months for maize per household 7 months for Groundnuts per household 6 months for Beans per household | Will be collected next 3rd Quarter |  |  |  |
|  | Amount of money spent on food per quarter by household type | 183,200 per household per quarter (12,103 Ugx spent on Simsim, 69,052 Ugx spent on maize, 39,154 Ugx spent on groundnuts, 20,401 Ugx spent on beans) | 173,400 Ugx per household per quarter (20,576 Ugx spent on Simsim 67,800 Ugx spent on maize, 43,272 Ugx spent on Groundnuts, 20,438 Ugx spent on beans) |  |  |  |
| Outcome 2 Improved income by 120 targeted farmers | Amount earned from sale of harvest in each harvest year | 462,500 Ugx | This is to be collected annually | 16 Individuals received saving and loans group trainings (7M, 9F) 120 individuals participated in saving and loans groups (68 F,52M) | 16 Individuals received saving and loans group trainings (7M, 9F) 120 individuals participated in saving and loans groups (68F,52M) | Training of VSLA group executives (chairperson, Secretary and Treasurer) on VSLA methodology) 16 (9F, 7M) Training of group executives on group Dynamics 12 (7M,5F) Support the VSLA groups with pass books 120 (68F, 52M) |
|  | % of households with an income above X amount by household type | X amount per household is 628,000 per household per annum | N/A |  |  |  |
|  | % of households who report an increased ability for 1 child in school | 43.3% | 33% |  |  |  |
|  | Average annual savings of VSLA groups | Kaemanik 985,000 Ugx Toiunae 1,577,500 Ugx Korisae 2,500,000Ugx Longayum Napetakeru 2,000,000 Ugx | This is collected annually |  |  |  |
| Outcome 3 Reduced cases of domestic violence related to handling of crop harvests ad incomes. | Number of reports and referrals by target farmers on domestic violence due to crop harvest and related incomes. | Referrals to LC1’s 25 CDO’s 05 Police (Kacheri) 07 | Referrals to LC1s 06 CDO 0 Police 04 | N/A | N/A | N/A |
|  | Changes in attitudes to SGBV by men, and community male leaders | Change in attitude indicators - Men and women work together unlike the previous years - Some men have started supporting their wives to open business - Fighting among men and women in houses have reduced - Relative decrease in divorce among men and women - Men have started engaging women in decision making - Men have started embracing education by sending children to school. |  |  |  |  |